## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3654596 | 68326 | ATM Project | 17 | ATM_1-17 | 292616 | Bug |  |  | 64015 | 1.1 | MFT-34 Account Inquiry Issue- Gives Unknown Error and $500 | The function being tested: THE ACCOUNT INQUIRY FUNCTION Initial State: The system is prepared to give inquiry information to the customer Steps to reproduce error: 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 4) Balance Inquiry then choose option 2) Savings. Expected Outcome: The system displays that, "you have no access to that account" Actual Outcome: The system displays an unknown error and gives the user $500 | 1 | Open | 2 | High | 64015 | 1.1 |  |  | 319791 | Lucas Ion | 319791 | Lucas Ion | Jan. 27, 2022 10:53 |  | 319791 | Lucas Ion | Jan. 28, 2022 20:34 | 0 | 0 | Jan. 27, 2022 10:54 Lucas Ion This issue still exists in version 1.1. However now it is doing the same error for the Savings account rather than Markets account
3654593 | 68326 | ATM Project | 16 | ATM_1-16 | 292616 | Bug |  |  | 64005 | 1.0 | Performing an account inquiry creates an unknown error | The function being tested: THE ACCOUNT INQUIRY FUNCTION Initial State: The system is on Steps to reproduce error: 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 4) Balance Inquiry then choose option 2) Money Market. Expected Outcome: The system displays that, "you have no access to that account" Actual Outcome: The system displays an unknown error and gives the user $500 | 3 | Resolved | 2 | High | 64005 | 1.0 |  |  | 319791 | Lucas Ion | 319791 | Lucas Ion | Jan. 27, 2022 10:51 |  | 319791 | Lucas Ion | Jan. 28, 2022 20:33 | 0 | 0
3654579 | 68326 | ATM Project | 14 | ATM_1-14 | 292616 | Bug |  |  | 64005 | 1.0 | Transfer - Transfering more money than is on the account | The function being tested: THE TRANSFER FUNCTION Initial State: The system is on Steps to reproduce error: 1. Launch the program 2. Select button ON at the right corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 3) Transfer 8. Choose option 1) Checking and then choose option 2) Deposit 9. Enter a very large number in pane (Ex. $1234567.00) Expected Outcome: An error would be displayed indicating that there is not enough money. Actual Outcome: The program froze, and needed to be restarted. | 2 | In Progress | 3 | Normal | 64005 | 1.0 |  |  | 319791 | Lucas Ion | 319791 | Lucas Ion | Jan. 27, 2022 10:28 |  | 319791 | Lucas Ion | Jan. 28, 2022 20:30 | 0 | 0 | Jan. 28, 2022 20:30 Lucas Ion This issue still persists in version 1.1
3654570 | 68326 | ATM Project | 13 | ATM_1-13 | 292616 | Bug |  |  | 64005 | 1.0 | Balance Inquiry - Unavailable Selection for Account Inquiry | The function being tested: THE ACCOUNT INQUIRY FUNCTION Initial State: The system is prepared to allow the customer to select which account they want to inquire from Steps to reproduce error: 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 4) Balance Inquiry. 8. Choose any option that is not available on the green screen. Expected Outcome: Nothing would happen until a correct button was selected Actual Outcome: The program froze, and needed to be restarted. | 3 | Resolved | 3 | Normal | 64005 | 1.0 |  |  | 319791 | Lucas Ion | 319791 | Lucas Ion | Jan. 27, 2022 10:22 |  | 319791 | Lucas Ion | Jan. 28, 2022 20:28 | 0 | 0
3654565 | 68326 | ATM Project | 12 | ATM_1-12 | 292616 | Bug |  |  | 64005 | 1.0 | Linux Machines Only - When entering an incorrect option for withdrawing money | The function being tested: THE WITHDRAW FUNCTION Initial State: The system is on Steps to reproduce error: 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 1) Withdrawal, then choose option 1) Checking to be withdrawal account. 8. Choose one of the following numbers: 0, 6, 7, 8, 9 Expected Outcome: Nothing would happen until a correct button was selected Actual Outcome: The program froze, and needed to be restarted. | 3 | Resolved | 3 | Normal | 64005 | 1.0 |  |  | 319791 | Lucas Ion | 319791 | Lucas Ion | Jan. 27, 2022 10:19 |  | 319791 | Lucas Ion | Jan. 28, 2022 20:28 | 0 | 0
3654583 | 68326 | ATM Project | 15 | ATM_1-15 | 292616 | Bug |  |  | 64015,64005 | 1.1,1.0 | MFT8- Incorrect Message Displayed when asking for another transaction | The function being tested: THE WITHDRAW FUNCTION Initial State: The system is on Steps to reproduce error: 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 1) Withdrawal, then choose option 1) Checking to be withdrawal account. 8. Choose any valid option. Expected Outcome: The system withdraws and displays on the green screen with the message: "Would you like to do another transaction?" Actual Outcome: The system withdraws and displays on the green screen with the message: " ** * Wood * ** you like to do another transaction?" | 3 | Resolved | 4 | Low | 64005 | 1.0 | 0 | Fixed | 319791 | Lucas Ion | 319791 | Lucas Ion | Jan. 27, 2022 10:36 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:41 | 0 | 0
3652493 | 68326 | ATM Project | 11 | ATM_1-11 | 292616 | Bug |  |  | 64015 | 1.1 | MFT - Savings Account Inquiry | **Initial State** : System is on and authenticated, Balance Inquiry transaction selected. **Step reproduce defect** : Select savings account from cards that are applicable. 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 4) Balance Inquiry, then choose option 2) Saving. **Expected outcome** : System prints correct receipt showing correct balance. **Actual outcome** : Displays "Unknown Error" and dispenses $500 dollars. Log shows transfer transaction. | 1 | Open | 3 | Normal |  |  |  |  | 319800 | Alden Lien | 319800 | Alden Lien | Jan. 26, 2022 22:37 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:31 | 0 | 0
3652460 | 68326 | ATM Project | 10 | ATM_1-10 | 292616 | Bug |  |  | 64015 | 1.1 | Withdraw - "$" missing in the dollar display | The initial state of the system: System is on Steps to reproduce: 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 1) Withdrawal, then choose option 1) Checking to be withdrawal account. Expected Outcome: All amounts of dollars have "$" in front of the number Actual Outcome: Option 3 is missing "$" | 1 | Open | 3 | Normal |  |  |  |  | 319792 | Hao Nguyen | 319792 | Hao Nguyen | Jan. 26, 2022 22:19 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:29 | 0 | 0
3652416 | 68326 | ATM Project | 9 | ATM_1-9 | 292616 | Bug |  |  | 64015 | 1.1 | MFT29 - Transfer 50 cents short | **Initial State** : **Step reproduce defect** : 1. Launch the program 2. Select button ON at the right corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 3) Transfer 8. Choose option 1) Checking and then choose option 2) Deposit 9. Enter a desired amount to transfer. **Expected outcome** : System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) **Actual outcome** : Incorrect updated balance and available ( 50 cents short) | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed | 319790 | LAB1-Group33 | 319790 | LAB1-Group33 | Jan. 26, 2022 21:57 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:27 | 0 | 0
3652386 | 68326 | ATM Project | 7 | ATM_1-7 | 292616 | Bug |  |  | 64015 | 1.1 | MFT14 - Withdrawal | **Initial State** : System is displaying the menu of withdrawal amounts, account balance is at $100.00 **Step reproduce defect** : 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option 1) Withdrawal, then choose option 1) Checking to be withdrawal account. 8. Choose option *1) $20.00*. **Expected outcome** : System dispenses this amount of cash; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back). **Actual outcome** : Withdrawal fails; System displays a message and asks customer to choose a lower amount. | 3 | Resolved | 3 | Normal |  |  | 0 | Fixed | 319790 | LAB1-Group33 | 319790 | LAB1-Group33 | Jan. 26, 2022 21:45 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:23 | 0 | 0 | Jan. 26, 2022 22:20 Alden Lien Defect is still present in version 1.1, "insufficient cash available" is displayed when entering a value less than the account balance.
3652323 | 68326 | ATM Project | 5 | ATM_1-5 | 292616 | Bug |  |  | 64005 | 1.0 | Withdrawal - Enter invalid money options | The initial state: The system is on Step to reproduce: Insert the card 1, enter Pin 42, choose 1 for Withdrawal, choose Checking, and then choose one of the following numbers: 0, 6, 7, 8, 9 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option *1) Withdrawal*, then choose option 1) Checking to be withdrawal account. 8. Choose one of the following numbers: 0, 6, 7, 8, 9 Expected outcome: The system prints out: "Incorrect input try again" and shows the options Actual outcome: The system gives animations of a $20 dollar bill printed out and the system stays on the dollar menu screen. | 2 | In Progress | 3 | Normal |  |  |  |  | 319792 | Hao Nguyen | 319792 | Hao Nguyen | Jan. 26, 2022 21:21 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:20 | 0 | 0 | Jan. 26, 2022 22:06 Hao Nguyen Defect still exists in version 1.1
3652271 | 68326 | ATM Project | 4 | ATM_1-4 | 292616 | Bug |  |  | 64005 | 1.0 | Card Number | **Initial State** : System is on and authorized as Card Pin 1 **Step reproduce defect** : 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose any transaction option, for example. *2) Deposit* 8. Choose option 1) Checking to be deposit account 8. Enter any amount as desired and click to "Click to insert envelope" **Expected outcome** : System displays the transaction completed on inputted card number (Card Pin 1). **Actual outcome** : System displays a different card number (inputted +1, e.g. card number 1 is inserted, transaction occurs on card number 2). | 2 | In Progress | 3 | Normal | 64005 | 1.0 |  |  | 319800 | Alden Lien | 319800 | Alden Lien | Jan. 26, 2022 21:09 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:18 | 0 | 0 | Jan. 26, 2022 22:04 Hao Nguyen Defect still exists in version 1.1
3651604 | 68326 | ATM Project | 2 | ATM_1-2 | 292616 | Bug |  |  | 64005 | 1.0 | Deposit | '- **Initial State** : System is on and after authorization state, the Total balance is at $100.00 - **Step reproduce defect**: 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option *2) Deposit* and then choose option *1) Checking* 8. Enter $30.00 as the desired amount to transfer, Click on "Click to insert envelope". - **Expected outcome:** System prints the receipt with Total Balance of $130.00 - **Actual outcome** : System prints the receipt with Total Balance of $120.00. (always $10.00 short). | 2 | In Progress | 2 | High |  |  |  |  | 319790 | LAB1-Group33 | 319790 | LAB1-Group33 | Jan. 26, 2022 14:51 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:11 | 0 | 0 | Jan. 26, 2022 22:17 LAB1-Group33 Defect has not been fixed in version 1.1. The Total Balance is 10 cents short
3651629 | 68326 | ATM Project | 3 | ATM_1-3 | 292616 | Bug |  |  | 64005 | 1.0 | Transfer | **Initial State** : System is on and after authorization state **Step reproduce defect** : 1. Launch the program 2. Select button ON at the right corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter 42 as the correct PIN. 7. Choose option *3) Transfer* 8. Choose option *1) Checking* and then choose option *2) Deposit* 9. Enter $30.00 as the desired amount to transfer. **Expected outcome** : System should print on the console log with the message includes that the system transfers money from Checking to Saving **Actual outcome** : System displays message of the transfer from Saving to Checking | 2 | In Progress | 2 | High |  |  |  |  | 319790 | LAB1-Group33 | 319790 | LAB1-Group33 | Jan. 26, 2022 15:14 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 10:08 | 0 | 0 | Jan. 26, 2022 22:19 LAB1-Group33 Defect still exists in version 1.1
3652384 | 68326 | ATM Project | 6 | ATM_1-6 | 292616 | Bug |  |  | 64005 | 1.0 | MFT40 - Re-enter PIN on Third Try | **Initial State** : System is on and card is inserted. Requesting PIN input. **Step reproduce defect** : 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter any number except "42" as the incorrect PIN **2 times** 7. Enter 42 as the correct PIN for the third time **Expected outcome** : Authorizes and displays transaction type selection on the green screen. **Actual outcome** : Prompts to re-enter PIN again. | 2 | In Progress | 3 | Normal |  |  |  |  | 319800 | Alden Lien | 319800 | Alden Lien | Jan. 26, 2022 21:44 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 00:28 | 0 | 0 | Jan. 26, 2022 22:08 Hao Nguyen Defect still exists in version 1.1 | Jan. 28, 2022 00:07 LAB1-Group33 The defect still exists on version 1.1
3652398 | 68326 | ATM Project | 8 | ATM_1-8 | 292616 | Bug |  |  | 64005 | 1.0 | MFT39 - Re-enter PIN on Second Try | **Initial State** : System is on and card is inserted. Requesting PIN input. **Step reproduce defect** : 1. Launch the program 2. Select button ON at the left corner of the window. 3. Enter any desired amount of $20 bills. 4. Select "Click insert card" 5. Enter Card number 1 6. Enter any number except "42" as the incorrect PIN 7. Enter 42 as the correct PIN **Expected outcome** : Authorizes and displays transaction type selection on the green screen. **Actual outcome** : Prompts to re-enter PIN again. | 2 | In Progress | 3 | Normal |  |  |  |  | 319800 | Alden Lien | 319800 | Alden Lien | Jan. 26, 2022 21:50 |  | 319790 | LAB1-Group33 | Jan. 28, 2022 00:28 | 0 | 0 | Jan. 26, 2022 22:17 Alden Lien Defect has not been fixed in version 1.1